## LESSONS LEARNED
LESSONS LEARNED
DOCUMENT VERSION: 1.0
PROJECT NAME | Data Driven Insights on Student Success Factors Analysis
PROJECT ID | IP-5496
PROJECT MANAGER | Harshada Topale
PROJECT SPONSOR | Tushar Topale
SL. NO | DATE RAISED | EVENT | LESSON CATEGORY | EARLY WARNING SIGNS? | RECOMMENDATIONS | ACTIONS | OWNER | STATUS | ADDITIONAL COMMENTS
1 | 2024-08-25 | Requirement Gathering | Communication | Lack of clarity on project objectives | Schedule a kick off meeting to clarify objectives | Meeting held on 28-08-2024 | Project Team Lead | Solved | Clear objectives helped align the Project Team Lead
2 | 2024-09-25 | Data Analysis | Time Management | Extended analysis phase due to complex data | Allocate more time for analysis | Adjusted timelines | Project Team Lead | Solved | Revised timelines led to better analysis outcomes
3 | 2024-10-04 | Final Review & Submission | Project Closure | Final submission | Begin preparation earlier in future projects | Early report preparation initiated | Project Team Lead | Solved | Timely submission achieved with all requirements met