## Project Schedule
Data Analytics Project Schedule
|  | PROJECT START DATE | 2024-08-24
|  | Display Week Sr No | 1 | [10 empty] | 2024-08-19 | [6 empty] | 2024-08-26 | [6 empty] | 2024-09-02 | [6 empty] | 2024-09-09 | [6 empty] | 2024-09-16 | [6 empty] | 2024-09-23 | [6 empty] | 2024-09-30 | [6 empty] | 2024-10-07 | [6 empty] | 2024-10-14
 | time axis 2024-08-19 to 2024-10-20
Sr No | Week/ Duration/ Sprint/ Phase | Activities | Task | Sub Task | Dependencies | Assigned to | Start Date | End Date | Actual End Date | Hours required | Status | Progress | Comments | time axis 2024-08-19 to 2024-10-20
1 | Phase - I
1.1 |  | Initial meeting | Requirement Gathering | Understanding project objectives, identifying data sources | None |  | 2024-08-24 | 2024-08-28 | 2024-08-28 | 10 | Completed | 10 | Successfully gathered requirements and data scope
1.2 |  | Review collected data | Data Collection | Collecting event attendance data, student details, event fields | Requirement analysis |  | 2024-08-29 | 2024-09-02 | 2024-09-02 | 12 | Completed | 20 | Data collected
1.3 |  | Data quality check, outlining cleaning process | Data Cleaning | Handling missing values, formatting data, removing irrelevant data | Data collected |  | 2024-09-03 | 2024-09-10 | 2024-09-10 | 15 | Completed | 30 | Data cleaned and prepared for analysis
1.4 |  | Reviewed dataset, discussed analysis methods | Data Analysis | Analyzing trends in attendance data | Cleaned data |  | 2024-09-11 | 2024-09-30 | 2024-09-30 | 25 | Completed | 55 | Analysis performed on student-event relationships
1.5 |  | Drafted key findings | Insights Generation | Generating key insights on student success factors | Data analysis |  | 2024-10-01 | 2024-10-02 | 2024-10-02 | 10 | Completed | 80 | Insights finalized
2 | Phase - II
2.1 |  | Report outline preparation, draft review | Report Preparation | Preparing final report with visualizations and key findings | Completed insights |  | 2024-10-03 | 2024-10-03 | 2024-10-03 | 8 | Completed | 95 | Report prepared and reviewed
2.2 |  | Final report review and approval | Final Review & Submission | Reviewing findings, making revisions and submitting the project | Prepared report |  | 2024-10-04 | 2024-10-04 | 2024-10-04 | 5 | Completed | 100 | Final project submitted on October 4, 2024
Note on H7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Nirbhey Singh Pahwa - I was thinking if we should add an actual start date column as well? Reply: Or, let's call this one as planned start date and the next one as start date. The same can be done for End date. Because, writing 'actual' feels as if we've missed some deadline of some sorts so can be avoided. You can have this in the DM Goals template for now, let me add this to the next version of this template, i.e., Goals [Template v0.5] Thank you